## Responsibility Matrix
Legend: ● = Primary responsibility ○ = Support ! = Unclear
RESPONSIBILITY MATRIX
# | Category | Activity / Scope | Company (Cairn) | Contractor (DBS) | SOW Ref. | Remarks | Comment
1 | A. Contract, Rig Asset & Insurance | Supply of complete drilling rig package (1000 HP & 750 HP), intact, fully functional and to Company specifications | ● |  | 2, 3.1
2 | A. Contract, Rig Asset & Insurance | Spare parts – 3-year stock (already procured) | ● | ○ | 3.1 | Company supplies; Contractor inventories, controls consumption and maintains stock
3 | A. Contract, Rig Asset & Insurance | Minimum 4 consecutive years of work | ● |  | 2 | Company guarantees the minimum contract for 4 years
4 | A. Contract, Rig Asset & Insurance | Planning wells within rig rated capacity; consequences of exceeding capacity (NPT, accidents, reduced efficiency) | ● | ○ | 2, 3.4.4 | Depth beyond rated capacity needs Contractor’s written consent
5 | A. Contract, Rig Asset & Insurance | Insurance of Contractor personnel and Contractor equipment |  | ● | 3.4.18 | Insurance of the Company-owned rig not stated | Clarify
6 | A. Contract, Rig Asset & Insurance | KPI definition and performance monitoring framework | ● | ● | 3.1 | KPIs to be set jointly
7 | A. Contract, Rig Asset & Insurance | Independent recording of rig data (separate from third-party service providers) |  | ● | 1
8 | A. Contract, Rig Asset & Insurance | Perform all work required to reach well objective, incl. supervision of and assistance to Company’s other contractors |  | ● | 3.4.5
9 | A. Contract, Rig Asset & Insurance | Right to inspect Contractor-operated equipment at any time (directly or via nominee); Contractor to permit and assist | ● | ○ | 3.4.35
10 | A. Contract, Rig Asset & Insurance | Right to reject equipment not meeting OEM/API or safety/hygiene requirements; Contractor to replace rejected equipment to Company’s satisfaction | ● | ● ! | 3.4.36 | UNCLEAR: replacement cost where rejected item is Company-owned rig equipment. | Clarify
11 | A. Contract, Rig Asset & Insurance | Consequence management for HSE, legal and road-safety non-compliance | ● |  | 10.63 | Per Cairn consequence management guidelines
12 | A. Contract, Rig Asset & Insurance | Liaison between Contractor Rig Manager and Company Technical Representative | ● | ● | 3.8
13 | B. Rig Receipt, Transport, Commissioning & Acceptance | Port reception and customs clearance at Indian port | ● |  | 3.1
14 | B. Rig Receipt, Transport, Commissioning & Acceptance | Transport of rig from port to first location | ● ! | ● ! | 1, 3.1 | UNCLEAR: Note 1 says Company transports and Contractor supervises; Section 3.1 says Contractor transports | Clarify
15 | B. Rig Receipt, Transport, Commissioning & Acceptance | Supervision of port-to-site transport |  | ● | 1
16 | B. Rig Receipt, Transport, Commissioning & Acceptance | Rig-up and function testing of the rig |  | ● | 3.1, 9
17 | B. Rig Receipt, Transport, Commissioning & Acceptance | Rectification of equipment deficiencies/design defects/non-fit-for-purpose items found during testing | ● | ○ | 3.1, 4.1, 9
18 | B. Rig Receipt, Transport, Commissioning & Acceptance | Execution of major/critical rectifications from pre-mobilization inspection | ● (cost) | ● (execute) | 7 | Contractor performs; cost to Company.
19 | B. Rig Receipt, Transport, Commissioning & Acceptance | Pre-mobilization and acceptance inspection (direct or third party) | ● | ○ | 4.1, 7, 9
20 | B. Rig Receipt, Transport, Commissioning & Acceptance | Audit plan submission (≥7 days before audit) and closure of Critical/Major findings |  | ● | 3.4.27, 4.1
21 | B. Rig Receipt, Transport, Commissioning & Acceptance | DROPS survey (third party) | ● |  | 4.1
22 | B. Rig Receipt, Transport, Commissioning & Acceptance | Closure of DROPS findings and ongoing DROPS management programme |  | ● | 4.1
23 | B. Rig Receipt, Transport, Commissioning & Acceptance | BOP shear-ram test on 5", 4", 3½" pipe before acceptance | ○ (witness) | ● ! | 3.4.9, 9.4 | Stated at Contractor’s cost although BOP is Company-owned and shearing of Drill Pipe | Clarify
24 | B. Rig Receipt, Transport, Commissioning & Acceptance | BOP / choke manifold / control unit valid certification (API 16A, 16C, 6A, 16D) before mobilization | ! | ● ! | 9.4 | Owner-rig obligation written onto Contractor | Clarify
25 | B. Rig Receipt, Transport, Commissioning & Acceptance | Valid certification & inspection reports at rig handover | ● |  | 3.4.3
26 | B. Rig Receipt, Transport, Commissioning & Acceptance | Maintaining valid certification & inspection reports during contract |  | ● | 3.4.3, 7
27 | B. Rig Receipt, Transport, Commissioning & Acceptance | 24-hour endurance test (drawworks, top drive, mud pumps, pipe handling) and crew competence demonstration | ○ | ● | 9.5 | 24-hour endurance testing | Discussion
28 | B. Rig Receipt, Transport, Commissioning & Acceptance | VSAT (G-force) analysis of shale shakers – before acceptance, every well / 6-monthly |  | ● | 3.4.51, 9.6
29 | B. Rig Receipt, Transport, Commissioning & Acceptance | Manpower for training, development and operation during commissioning |  | ● | 3.1
30 | B. Rig Receipt, Transport, Commissioning & Acceptance | Written notice of acceptance to commence operations | ● |  | 9.2 | Day Rate commencement ? | Discussion
31 | B. Rig Receipt, Transport, Commissioning & Acceptance | Ensure all equipment is fit for immediate service before sent to site (e.g. breaking-in of new drill strings) | ● |  | 3.4.37
32 | B. Rig Receipt, Transport, Commissioning & Acceptance | Drill pipe, handling tools, crossovers & well-control equipment: 5", 3½", 2⅞" DP; 21¼" 2K diverter system; 20¾" 3K BOP stack (2K annular, 3K double ram, VBR 2⅞"–5½"), spools, test stump, cup tester, 20" casing bowls | ! | ! | 3.13 | CRITICAL – company not stated. Rental to be charged back to the company | Clarify
33 | B. Rig Receipt, Transport, Commissioning & Acceptance | Full DS-1 Category 4 inspection of drill string before contract start-up | ! | ● ! | 7 (Table 1) | Not required for new string with valid certificates. Cost on Company-owned string to be clarified | Clarify
34 | B. Rig Receipt, Transport, Commissioning & Acceptance | Second survey before operations to confirm close-out of first survey; additional audits as deemed fit | ● | ○ | 7
35 | B. Rig Receipt, Transport, Commissioning & Acceptance | Furnish all material/inspection reports before rig inspection (manufacturer/3rd-party reports, lifting gear, pressure vessels, relief valves, NDT of HP pipework and structural welds) | ○ | ● ! | 9.3 | Company to hand over OEM/asset documents for Company-owned rig | Clarify
36 | B. Rig Receipt, Transport, Commissioning & Acceptance | Year of manufacture and certification for all main rig equipment; 3 years inspection & maintenance history; usage history of last 3 contracts; TPIA report ≤6 months | ! | ● ! | 7, QA/QC | Company holds this data for its own rig | Clarify
37 | B. Rig Receipt, Transport, Commissioning & Acceptance | Inspection Schedule Matrix and detailed plan/time for major inspections |  | ● | 7 | Frequencies per Tables 1–3 (see ‘Inspection Tables’ sheet).
38 | B. Rig Receipt, Transport, Commissioning & Acceptance | Material certificates for procured items: EN 10204 3.1/3.2 (critical), 2.2 (others); no 2.1 without approval |  | ● | QA/QC
39 | C. Rig Moves & Logistics | Decision to move, planning, sequencing and execution of all rig moves |  | ● | 4, 4.3 | Consult Company on transport conditions
40 | C. Rig Moves & Logistics | Cranes, forklifts, trailers, MHE (min. 18 trailers, 4 × >40 t cranes, 10 t forklift) |  | ● | 4 | Zero rig-move rate if not on site
41 | C. Rig Moves & Logistics | Minimum rig-move crew (Driller, AD, Derrickman, 2 Roustabouts, 2 Transport Managers, 2 FLT and 6 crane operators) |  | ● | 4 | Zero rate if not met
42 | C. Rig Moves & Logistics | Route survey and signed route map | ○ | ● | 4 | Joint with Company transport supervisor
43 | C. Rig Moves & Logistics | Rig spotting on correct slot/cellar and toolpusher sign-off | ○ (format) | ● | 4
44 | C. Rig Moves & Logistics | Rig mats and support beams for spotting on cellar |  | ● ! | 3.1 | Rig mats to be included in the Rig package | Discussion
45 | C. Rig Moves & Logistics | Anchor points for guy lines |  | ● ! | 4 | To be provided by the contractor preparing the drill site location | Discussion
46 | C. Rig Moves & Logistics | Transport of Company & subcontractor equipment during moves (10–12 × 40 ft loads) |  | ● | 4, 4.3
47 | C. Rig Moves & Logistics | Vacuum/suction trucks for transfer of left-over fluids | ● |  | 4.4
48 | C. Rig Moves & Logistics | Safe handling of chemicals/fluids in transit; MSDS and TREM cards with drivers |  | ● | 4.4
49 | C. Rig Moves & Logistics | Construction of approach road to drill site | ● |  | Annex III-6
50 | C. Rig Moves & Logistics | Foundations, civil works, cellars and soak pits | ● |  | 3.7, Annex III-11 | Earth pit to be included
51 | C. Rig Moves & Logistics | Demobilization within 14 days of termination; rig handed back in current working condition |  | ● | 4.2
52 | C. Rig Moves & Logistics | Rig-move sub-contractor to meet Company minimum requirements (Annexure A) | ○ | ● ! | 4 | Annexure A requirements document not provided with SOW | Clarify
53 | C. Rig Moves & Logistics | Standard documented rig-move procedures; advise Company of number, size and weight of loads and optimum load sequence |  | ● ! | 4 | To be provided by the company | Discussion
54 | C. Rig Moves & Logistics | Preliminary visits to locations; confirm dimensions, suitability and accessibility of Company-provided location |  | ● | 4, 9.2
55 | C. Rig Moves & Logistics | Achieve target rig-move times (Annexure A table); daylight-only moves |  | ● | 4 | Excess time = NPT; faster = efficiency credit | Clarify
56 | C. Rig Moves & Logistics | Nipple-up of diverter and make-up of surface-section stands as part of rig move |  | ● | 3.1, 4.5 | Day Rate starts after rig acceptance ? | Clarify
57 | C. Rig Moves & Logistics | Skidding package / walking system for multi-slot pads (8 m spacing, 12–14 slots per row) | ● ! |  | 3.1 | Should be a part of company scope or Rig package | Clarify
58 | C. Rig Moves & Logistics | Operation and maintenance of cranes and oilfield haulers/trailers |  | ● | Annex III-9
59 | C. Rig Moves & Logistics | Assembling (rig-up) and dismantling (rig-down) of rig equipment |  | ● | Annex III-12, 14
60 | D. Drilling, Completion & Well Operations | Well programme, drilling operational plans, job programmes | ● | ○ | 3.4.6, 9 | Contractor comments before spotting
61 | D. Drilling, Completion & Well Operations | Maps, location info, soil boring, geological data, trajectory, suspension/abandonment policy | ● |  | 9
62 | D. Drilling, Completion & Well Operations | Wellhead information and running instructions | ● |  | 9 | Via Company’s third-party contractor
63 | D. Drilling, Completion & Well Operations | 24/7 drilling operations as per Company programme within rig capacity |  | ● | 3.2, 3.4.1
64 | D. Drilling, Completion & Well Operations | Completion and workover operations (kill, scraper, displacement, fishing, milling, squeeze, packers, TCP/DST, activation) | ● (provide) | ● (execute) | 3.3, 3.4.8 | Tools provided by the company, executed by the contractor | Discussion
65 | D. Drilling, Completion & Well Operations | Running, landing and testing of casing, liner and tubing; storage and handling |  | ● | 3.4.28
66 | D. Drilling, Completion & Well Operations | Supply of casing, tubing, wellheads and consumable well materials | ●
67 | D. Drilling, Completion & Well Operations | Cleaning, drifting and measuring Company casing/tubing on site |  | ● | 3.9
68 | D. Drilling, Completion & Well Operations | Install, test, maintain and operate BOP; pressure tests of wellheads, casing, BOPs | ○ (witness) | ● | 3.4.9, 3.4.30, 3.10
69 | D. Drilling, Completion & Well Operations | Well-control bridging document | ● | ● | 3.4.16, 9 | Mutually agreed.
70 | D. Drilling, Completion & Well Operations | Primary well shut-in; kill sheets, pre-kick sheets, trip sheets |  | ● | 3.11, 6.10
71 | D. Drilling, Completion & Well Operations | IWCF/IADC-certified supervisor on drill floor at all times |  | ● | 3.4.24
72 | D. Drilling, Completion & Well Operations | Drilling & completion fluid chemicals and additives | ● |  | 3.4.7
73 | D. Drilling, Completion & Well Operations | Mixing, conditioning, monitoring and control of drilling/completion fluids (incl. synthetic OBM) |  | ● | 3.2, 3.4.31
74 | D. Drilling, Completion & Well Operations | Specialist third-party services (cementing, logging, DD, MWD/LWD, coring, wireline, perforation) | ● | ○ | 3.4.33 | Contractor supports and assists
75 | D. Drilling, Completion & Well Operations | Fishing tools for Contractor equipment and tubulars | ! | ! | 3.4.13 |  | Clarify
76 | D. Drilling, Completion & Well Operations | Cold casing cutting equipment with operator | ● |  | 3.4.46 | Contractor performs cutting operation | Clarify
77 | D. Drilling, Completion & Well Operations | Hydraulic torque equipment with operator | ● | ! | 3.4.47 | Third party or contractors crew | Clarify
78 | D. Drilling, Completion & Well Operations | Deviation surveys using rig equipment | ● | ! | 3.4.15 | Deviation tool to be provided by company | Discussion
79 | D. Drilling, Completion & Well Operations | Collection of cuttings/cores | ○ (containers) | ● | 3.4.32 | Third party or contractors crew | Clarify
80 | D. Drilling, Completion & Well Operations | Auto-driller monitoring (ROP, RPM, WOB, ΔP, torque) and export of setpoints |  | ● | 3.1
81 | D. Drilling, Completion & Well Operations | Continuous hydrocarbon and H₂S gas detection |  | ● | 3.4.29 | Rig instrumentation to have H₂S gas detection system | Discussion
82 | D. Drilling, Completion & Well Operations | Written operating procedures (rig move/rig-up/mast raising, BOP testing & flow checks, emergencies, maintenance, tripping, BHA, casing, cut & slip, mud pumps, auxiliary brake, trip tank/pit monitoring, chemicals, power generation) |  | ● | 3.9
83 | D. Drilling, Completion & Well Operations | Self-audit against agreed procedures and written reports; MOC policy applied to all equipment/procedure changes | ○ | ● | 3.9
84 | D. Drilling, Completion & Well Operations | Measure and record lengths and dimensions of all equipment and materials run in hole (Contractor, subcontractor or Company) |  | ● | 3.4.14
85 | D. Drilling, Completion & Well Operations | Suspend operations and notify Company when progress deviates from programme; make efforts to overcome difficulties |  | ● | 3.4.20
86 | D. Drilling, Completion & Well Operations | Notify Company of lost circulation or significant ROP change and act per agreed procedures |  | ● | 3.4.21 | Cost to company
87 | D. Drilling, Completion & Well Operations | Keep rig level and centred over well bore; suspend, make safe, notify and propose remedial action | ○ (approve) | ● | 3.4.23
88 | D. Drilling, Completion & Well Operations | Prepare for casing, liner and tubing runs, incl. confirming hanger, wellhead equipment and spares on site | ○ (witness) | ● | 3.11
89 | D. Drilling, Completion & Well Operations | Services associated with fishing operations | ● | ○ (execute) | 3.11 | As per instruction from company
90 | D. Drilling, Completion & Well Operations | Pressure tests to Company standards and programme; test charts; 30-minute advance notice; Company endorsement of each test | ○ (approve) | ● | 3.10
91 | D. Drilling, Completion & Well Operations | BOP testing diagrams before tests; full function test of stack & control system before pressure testing |  | ● | 6.8
92 | D. Drilling, Completion & Well Operations | Floor-O-Matic and Crown-O-Matic fully working 24×7 and function-tested each shift |  | ● | 3.4.45
93 | D. Drilling, Completion & Well Operations | Drawworks braking system fully functional per OEM throughout operations; Company periodic function tests | ○ | ● | 3.4.49
94 | D. Drilling, Completion & Well Operations | Auto-driller: monitor sensor data quality and safe disable; travelling block/top drive minimum-height disable |  | ● | 3.1
95 | D. Drilling, Completion & Well Operations | Brake-handle motors/actuators certified for Division 1 / Zone 1, −40°C to +60°C |  | ● | 3.1
96 | D. Drilling, Completion & Well Operations | Service and maintain shale shakers, desander, desilter and mud cleaner to best operating condition |  | ● | 3.4.51
97 | D. Drilling, Completion & Well Operations | Tank for collection and disposal of oil products/crude; no dumping of oils into waste pit |  | ● | 3.12
98 | D. Drilling, Completion & Well Operations | Familiarise key personnel with Company Emergency Procedures; conduct, report and record drills |  | ● | 3.8
99 | D. Drilling, Completion & Well Operations | Maintain drill-site surfaces; protect topsoil bearing capacity and drainage; prevent spills and leaks |  | ● | 3.4.17
100 | E. Maintenance, Spares & Consumables | Daily, planned, preventive, predictive and breakdown maintenance under ILM, with CMMS and digital KPI dashboards |  | ● | 3.1, 3.4.2, 7 | Frequencies per Annexure I.
101 | E. Maintenance, Spares & Consumables | Maintenance window beyond 1 hr/day (30 hr/month) | ○ (approve) | ● | 3.1
102 | E. Maintenance, Spares & Consumables | Repair of major damage without Contractor fault, or from design flaws | ● |  | 3.1
103 | E. Maintenance, Spares & Consumables | Major repair / overhaul of equipment | ! | ● ! | Annex III-5 vs 3.1 | Discussion | Clarify
104 | E. Maintenance, Spares & Consumables | Periodic inspections & NDT per Tables 1–3 (DS-1, API 7G-2, 8B, 4G, 16A, 7K, 16D) | ! | ● | 7 | Cost of Cat IV and 5-year recertifications on Company asset | Clarify
105 | E. Maintenance, Spares & Consumables | Fast consumables (grease, oils, hydraulic fluids, hoses, rings, filters) |  | ● | 3.1
106 | E. Maintenance, Spares & Consumables | Critical spares redundancy (mud pumps, power, top drive, BOP/well control) | ! | ● | 3.1, 3.4.25 | Overlaps Company’s 3-year spares- funding to be clarified | Clarify
107 | E. Maintenance, Spares & Consumables | Shaker and mud-cleaner screens (API 20–325 mesh) |  | ● | 3.4.52 | Chargable or Non-Chargable ? | Clarify
108 | E. Maintenance, Spares & Consumables | Hose register; HP piping wall-thickness and metallurgy records |  | ● | 3.4.42, 3.4.44
109 | E. Maintenance, Spares & Consumables | Lifting gear register, half-yearly colour coding, 6-monthly MPI, annual load test |  | ● | 3.4.34, 10
110 | E. Maintenance, Spares & Consumables | Calibration of gauges, weight indicator, PRVs (6-monthly) |  | ● | 10
111 | E. Maintenance, Spares & Consumables | Sharing backup tools across Company rigs at no additional cost | ● | ○ | 3.4.43
112 | E. Maintenance, Spares & Consumables | Painting, cleaning and chipping of rig equipment |  | ● | Annex I-31 | As per Company instructions.
113 | E. Maintenance, Spares & Consumables | Log books for engines, emergency generator, top drive, drawworks, hoisting equipment, rotary table, mud pumps, shale shakers (last overhaul and type) |  | ● | 6.19
114 | E. Maintenance, Spares & Consumables | Detailed maintenance checks per Annexure I (31 tasks, daily to monthly) | ○ (verify) | ● | Annex I
115 | E. Maintenance, Spares & Consumables | Only calibrated equipment/instruments; hazardous-zone certified electrical items and cables; IP-rated ‘open to atmosphere’ instruments |  | ● | QA/QC
116 | E. Maintenance, Spares & Consumables | Quarantine of non-conforming or transport-damaged items until resolved; min. 5% payout withheld for unresolved issues | ○ | ● | QA/QC
117 | E. Maintenance, Spares & Consumables | Technical changes only via Technical Query route | ○ (approve) | ● | QA/QC
118 | E. Maintenance, Spares & Consumables | Rig accessories compatible with production fluid characteristics; crude assay from Company | ○ | ● | QA/QC
119 | E. Maintenance, Spares & Consumables | Follow and demonstrate OEM storage/preservation requirements |  | ● | QA/QC
120 | E. Maintenance, Spares & Consumables | Spare PPE list maintained; handed to Company at pre-spud and monthly |  | ● | 3.4.25
121 | F. Fuel, Water, Utilities, Camp & Waste | Diesel supply and transport for rig, site, camp, cranes, forklifts and vehicles (incl. during moves) |  | ● | 3.6 |  | Discussion
122 | F. Fuel, Water, Utilities, Camp & Waste | Diesel to Company’s subcontractors |  | ● | 3.6 |  | Discussion
123 | F. Fuel, Water, Utilities, Camp & Waste | PESO storage licence; PESO-certified Form XIX bowser | ○ | ● | 3.6 |  | Discussion
124 | F. Fuel, Water, Utilities, Camp & Waste | Groundwater extraction permit | ● | ○ | 3.5
125 | F. Fuel, Water, Utilities, Camp & Waste | Drill water supply incl. water-well boring; salinity checks |  | ● | 3.5 | Company | Discussion
126 | F. Fuel, Water, Utilities, Camp & Waste | Potable water (4-day stock) and bottled drinking water for all at site & camp (7-day stock) |  | ● | 3.5 | Bottled drinking water by contractor | Discussion
127 | F. Fuel, Water, Utilities, Camp & Waste | Electricity and lighting at site and camp, incl. Company & third-party cabins |  | ● | 3.4.10
128 | F. Fuel, Water, Utilities, Camp & Waste | Camps (central + mini, 120 beds per rig), catering, housekeeping and lodging | ! | ● | 3.1, 3.4.10–11 vs Annex III-20/21 | Annex III shows drill-site accommodation under Company | Discussion
129 | F. Fuel, Water, Utilities, Camp & Waste | Boarding & lodging of Company personnel during pre-acceptance inspection |  | ● | 7 | Offset against free man-day allowance
130 | F. Fuel, Water, Utilities, Camp & Waste | Warehouse land and facilities |  | ● | 3.4.11 |  | Discussion
131 | F. Fuel, Water, Utilities, Camp & Waste | Rig & camp waste segregation, storage and disposal; hazardous waste via licensed vendor; septic overflow |  | ● | 3.7, 10
132 | F. Fuel, Water, Utilities, Camp & Waste | Disposal of drill cuttings, waste mud, and waste from Company & its contractors | ● |  | 3.7
133 | F. Fuel, Water, Utilities, Camp & Waste | Site cleaning before leaving; drain channels; spill prevention; 750-micron liners; secondary containment |  | ● | 3.4.50, 3.7, 3.12
134 | F. Fuel, Water, Utilities, Camp & Waste | Pollution control at drill site | ● | ○ | Annex III-19 | Contractor still does stack/noise monitoring
135 | F. Fuel, Water, Utilities, Camp & Waste | Security at drill site | ● |  | Annex III-18
136 | F. Fuel, Water, Utilities, Camp & Waste | Field communication between drill site and Company base | ● | ● | Annex III-10
137 | F. Fuel, Water, Utilities, Camp & Waste | Maintain minimum operational drill-water stock considering severe losses |  | ● | 3.5 | Company to provide drill-water | Discussion
138 | F. Fuel, Water, Utilities, Camp & Waste | Cost of all vehicles and equipment of Contractor and its sub-contractors |  | ● | 3.6
139 | F. Fuel, Water, Utilities, Camp & Waste | Colour-coded waste segregation; green-waste recycling; no waste discarded without Company knowledge |  | ● | 3.7
140 | G. Manpower, Competency & Welfare | Deployment of complete O&M crew and competency management |  | ● | 3.1, Annex II
141 | G. Manpower, Competency & Welfare | Key-personnel CVs and org chart; interview and approval of changes | ○ | ● | 3.8 |  | Clarify
142 | G. Manpower, Competency & Welfare | Full-time HSE engineer (≥5 yrs), 365 days |  | ● | 10
143 | G. Manpower, Competency & Welfare | 24-hr rig medic (MBBS, ≥2 yrs) and ALS ambulance with driver |  | ● | 10, Annex III-16
144 | G. Manpower, Competency & Welfare | Personnel transport (origin ↔ accommodation ↔ site) and area/entry permits |  | ● | Annex III-1 to 3
145 | G. Manpower, Competency & Welfare | Statutory licences (labour licence etc.) | ○ | ● | 3.4.19 | Other than statutory licences ? | Clarify
146 | G. Manpower, Competency & Welfare | Police clearance, pre/periodic medicals, DGMS Form O, food-handler checks |  | ● | 10
147 | G. Manpower, Competency & Welfare | Trainings: HSE induction, H₂S, confined space, WAH, fire/SCBA, PTW, defensive driving, MVT | ● |  | 10 (training table) | Cairn scope. Will this be charged to the contractor ? | Clarify
148 | G. Manpower, Competency & Welfare | Trainings: first aiders, crane/FLT operators, riggers, lift planner, signalman, TTT, RCA, IMS auditor, gas tester |  | ● | 10 (training table) | Cairn-approved agencies. Charge back to company ? | Clarify
149 | G. Manpower, Competency & Welfare | PPE for all Contractor and subcontractor personnel |  | ● | 10
150 | G. Manpower, Competency & Welfare | Medical treatment costs for Contractor personnel injured or ill at work | ○ | ● | 10
151 | G. Manpower, Competency & Welfare | Monthly personnel report (name, DOB, nationality, position, courses, experience, planned training) and monthly deployment report with invoice vs contractual manpower |  | ● | 6.18
152 | G. Manpower, Competency & Welfare | Radio operator: daily POB report and emergency contact sheet after last transport departs |  | ● | 6.6 | Implies radio operator/communication staff in crew. Radio communication to be provided
153 | G. Manpower, Competency & Welfare | Tie-up with nearest hospitals in operational area for emergency medical support; Company may assist in mobilising injured person | ○ | ● | 10.17–18
154 | G. Manpower, Competency & Welfare | Medical fitness tests for personnel working at height per Cairn requirements |  | ● | 10.15
155 | G. Manpower, Competency & Welfare | Two certified first aiders per shift |  | ● | 10 (training table)
156 | G. Manpower, Competency & Welfare | Senior management (technical & HSE) at monthly HSE meetings; HSE staff at daily meetings; Visible Felt Leadership site visits |  | ● | 10.64, 10.66
157 | G. Manpower, Competency & Welfare | Protective clothing; instruction on antidotes, first aid and chemical data sheets |  | ● | 3.8
158 | H. HSE Equipment & Systems | Caustic soda handling system and big-bag lifting/piercing device (zero exposure) |  | ● | 3.1 | Hydra w/ Jumbo bag shearing system on mixing hopper | Discussion
159 | H. HSE Equipment & Systems | 12 SCBA sets, fire extinguishers (IS 2190), gas detectors, personal H₂S/CO monitors, escape masks, breathalyser, lux & noise meters |  | ● | 10 | Fire extinguishers and others to be included with the rig package | Clarify
160 | H. HSE Equipment & Systems | AFDSS on all IC engines and exhaust insulation |  | ● ! | 10 | Retrofit on Company engines- clarify cost | Clarify
161 | H. HSE Equipment & Systems | Intrinsically safe CCTV (1-month backup) and hands-free talkback |  | ● | 10 | Provided by company, maintained by contrator | Discussion
162 | H. HSE Equipment & Systems | Scaffolding, fixed fall arrestors, push poles (6), non-spark hammers, impact gloves, insulated OHL stick |  | ● | 3.4.38–48, 10
163 | H. HSE Equipment & Systems | DG set with acoustic enclosure; stack & noise monitoring; monthly noise/illumination survey |  | ● | 10 |  | Clarify
164 | H. HSE Equipment & Systems | Annual HSE plan, ERP, EMP and HSE bridging document | ○ (approve) | ● | 10
165 | H. HSE Equipment & Systems | Incident reporting (12 h notice, 24 h preliminary, 7 working days full report) |  | ● | 10
166 | H. HSE Equipment & Systems | HSEQ, IMS and VSAP audits | ● | ○ | 10 | Contractor supports and closes findings (7 days for leading indicators)
167 | H. HSE Equipment & Systems | Comply with Cairn HSEQ policies, Zero Tolerance Behaviours, Life Saver Rules, Fatal Risk Control Standards, General HSE Conditions and Drilling Contractor HSE Requirements | ○ (provide docs) | ● | 10
168 | H. HSE Equipment & Systems | Road Transport Safety Policy incl. VTS in all LMV/HMV; Journey Management Procedure; Drug & Alcohol Policy |  | ● | 10
169 | H. HSE Equipment & Systems | Vehicle/trailer loads not to exceed 4.2 m height (overhead line clearance) |  | ● | 10
170 | H. HSE Equipment & Systems | Statutory reports and returns to government authorities | ○ | ● | 10.11 | With the approval and agreement of company
171 | H. HSE Equipment & Systems | Provide own HSE policies, procedures and records on request |  | ● | 10.12
172 | H. HSE Equipment & Systems | Zone I/II compliance (OMR’17, DGMS, OISD, API 500/505) and OISD 189 fire safety | ! | ● ! | 10.20–21 | Any upgrade needed on Company rig equipment - clarify cost | Clarify
173 | H. HSE Equipment & Systems | PESO certificates for all gas cylinders; 5-yearly hydrotest of pressure vessels/cylinders by PESO-approved agency |  | ● | 10.24–25
174 | H. HSE Equipment & Systems | Flow-line safety restraint systems on HP lines |  | ● | 10.27
175 | H. HSE Equipment & Systems | Mobile Crane Safety Procedure, Lifting & Hoisting Procedure, Green Hat Policy |  | ● | 10.28–31
176 | H. HSE Equipment & Systems | Maintain, repair and replace PPE; PPE issue records monthly |  | ● | 10.47
177 | H. HSE Equipment & Systems | Handrails on tanks/vessels >1.8 m; certified anchor points (MPI/load tested); full-body harnesses | ! | ● ! | 10.69–70 | Fabrication on Company tanks- clarify cost | Clarify
178 | H. HSE Equipment & Systems | COVID-19/Government health guideline compliance at Contractor cost |  | ● | 10.68
179 | H. HSE Equipment & Systems | Work permits (hot work, isolation, confined space, heights) and isolation policy | ○ (issuing authority) | ● | 6.11, Annex IV-3
180 | H. HSE Equipment & Systems | Weekly safety meeting reports, JSAs and risk assessments, safety equipment inspections, incident reports, safety award records, monthly statistics |  | ● | 6.22
181 | H. HSE Equipment & Systems | Report all near misses, however trivial |  | ● | 6.22
182 | H. HSE Equipment & Systems | HSE KPIs per Annexure IV (lagging indicators, mock drills, permits, accident accountability, leading indicators, housekeeping) | ○ (score) | ● | Annex IV
183 | I. Reporting, Documentation & Quality | Report formats | ● | ○ | 5 | Company formats to be used
184 | I. Reporting, Documentation & Quality | Daily reports: IADC, toolpusher (06:00), parameter charts, POB, BOP tests, space-out, BHA, bit, surveys, casing tally, daily tickets | ○ (sign) | ● | 6
185 | I. Reporting, Documentation & Quality | Monthly reports: performance/downtime, personnel, strategic stock, HSE statistics, lost-in-hole |  | ● | 6
186 | I. Reporting, Documentation & Quality | Technical Information File and drawings (layout, safety layout, fire-fighting, mud system, BOP stack-up) | ○ | ● | 8, 9
187 | I. Reporting, Documentation & Quality | Quality system (ISO 9001 / API Q1 / Q2), quality manual, TPIA report ≤6 months |  | ● | 10 (QA/QC) | Company or contractor ? | Clarify
188 | I. Reporting, Documentation & Quality | Non-compliant rig specification declaration |  | ● | 8
189 | I. Reporting, Documentation & Quality | Reports in English, legible, black ink; Company-agreed units |  | ● | 5
190 | I. Reporting, Documentation & Quality | Meal tickets signed daily, sent weekly with supporting documents | ○ (sign) | ● | 6.16
191 | I. Reporting, Documentation & Quality | Lost-in-hole technical investigation report (incl. radioactive source details) | ● | ● | 6.21 | Joint investigation
192 | I. Reporting, Documentation & Quality | Any other reports requested by Company Site Representative |  | ● | 6.23
193 | I. Reporting, Documentation & Quality | Modified/updated drawings submitted for Company approval and incorporation into contract | ○ (approve) | ● | 9
194 | I. Reporting, Documentation & Quality | Records and documentation per Annexure V checklist | ○ (verify) | ● | Annex V
195 | I. Reporting, Documentation & Quality | Rig Day Rate commencement |  |  |  |  | Discussion